## Slide 1
MALLANET
One platform for
many response sites
Multi-incident architecture, safe migration, and rapid-response operations
Shareable plan · August 2026
terremotocolombia.co → reusable platform
Notes: Open with the mission: preserve the proven Colombia response while creating a reusable operating platform.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md

## Slide 2
WHY CHANGE
The current system works—but each new response still starts too manually
MALLANET · MULTI-INCIDENT PLATFORM
02
The plan converts a successful single-response stack into repeatable infrastructure without interrupting Colombia.
01
Identity is compiled
A new event/domain currently needs configuration-specific builds, CORS changes, and deployment work.
02
Authority is global
Existing roles, invitations, and system-admin shortcuts are not safe foundations for a second organization.
03
Operations are manual
Provisioning, communications, migration, and release checks depend on hand-run steps and tribal knowledge.
Notes: Frame this as an operational scaling problem, not a rewrite for its own sake.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md

## Slide 3
PLATFORM MODEL
The target model separates reusable platform capability from response identity
MALLANET · MULTI-INCIDENT PLATFORM
03
One codebase and shared backend; each hostname receives an approved deployment configuration and an explicit event scope.
terremotocolombia.co
Deployment → Colombia incident
Brand · navigation · modules
terremotovenezuela.app
Deployment → Venezuela incident
Brand · navigation · modules
Trusted hostname resolution
Shared platform
Contracts · tenant-scoped services · modules · providers
queues · records · maps · communications · observability
Cross-event visuals use approved aggregate projections—not broad record access.
Notes: Emphasize that domains select approved deployment configuration; the browser does not choose tenant authority.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#runtime-deployments-and-communications
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-diagrams.md

## Slide 4
SYSTEM ARCHITECTURE
Four boundaries keep speed from weakening isolation
MALLANET · MULTI-INCIDENT PLATFORM
04
1
Experience
Public sites, organization admin, Mallanet operations console
2
Trusted authority
Exact host → deployment → allowed/default incident → immutable TenantScope
3
Platform services
Module gates, scoped repositories, adapters, queues, cache policies
4
Authoritative state
Neon Postgres, domain-owned records, configuration and operation ledgers
Rule: every ordinary request resolves exactly one organization + incident scope before data or cache access.
Notes: [Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-diagrams.md#1-complete-component-topology

## Slide 5
EVENT DETECTION
Signals create evidence and candidates—humans decide whether to launch
MALLANET · MULTI-INCIDENT PLATFORM
05
USGS + approved sources
Versioned adapters
Observations
Immutable revisions + health
Hazard events
Deterministic correlation
Incident candidate
Rules + reasons + replay
Human review
Approve, reject, suppress
Preview only
Activation is a separate approval
Source outage or silence changes source health—not public incidents.
Notes: Detection remains review-only in the first operating stages; it cannot route traffic or send notifications.
[Sources]
- https://earthquake.usgs.gov/earthquakes/feed/v1.0/geojson.php
- https://earthquake.usgs.gov/fdsnws/event/1/
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#hazard-signals-and-incident-candidates

## Slide 6
RECORDS & RELATIONSHIPS
Family reunification keeps identity, relationships, and disclosure as separate decisions
MALLANET · MULTI-INCIDENT PLATFORM
06
Source records
Missing · patient · unidentified · imports
PRN registry
Incident-scoped durable identity
Match proposals
Deterministic evidence only
Human review
Confirm · reject · unsure
Identity cluster
Reversible computed projection
Relationship assertions
PRN ↔ PRN · reviewed · reversible
Tracing and reunification cases
Contact, disclosure, handoff, reunion
A relationship never merges identity. A match never automatically publishes location or contact.
Notes: The plan borrows separation-of-concerns patterns, not genealogy-specific product scope.
[Sources]
- https://www.familysearch.org/innovate/data-model
- https://developers.familysearch.org/main/docs/gedcom-x
- https://familylinks.icrc.org/privacy-policy
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#architecture-research-synthesis

## Slide 7
RAPID RESPONSE LAUNCH
A response launches through a resumable provisioning ledger—not a checklist in someone’s head
MALLANET · MULTI-INCIDENT PLATFORM
07
1
Plan
Manifest validates identity, domains, modules, providers, roles, budgets
2
Preview
Protected site, synthetic data, channels off, isolation and rollback tests
3
Activate
Distinct approval; route, reads, writes, producers, then notifications
CHANNEL REGISTRY
WhatsApp discovery
Verified group/community invitation; manual step allowed
WhatsApp Business
Approved one-to-one/template messaging provider
Other channels
Email · SMS · social · forms · webhooks · partners
Notes: Ordinary WhatsApp group/community creation is not assumed to be automatable; unsupported work remains a verified waiting-external checkpoint.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#tenant-and-incident-operations
- https://www.postman.com/meta/whatsapp-business-platform/overview

## Slide 8
GOVERNANCE & ADMIN
Platform and response administration remain separate
MALLANET · MULTI-INCIDENT PLATFORM
08
PLATFORM SCOPE
Mallanet operations
Organizations · deployments · releases
source/provider health · readiness
security · support · aggregate reporting
ORGANIZATION SCOPE
Organization governance
Membership · recovery · role templates
policies · response inventory
channel ownership · org aggregates
INCIDENT SCOPE
Incident command
Modules · volunteers · content · queues
cases · providers · readiness
approved communications
Platform staff do not gain tenant-data access. Support requires an exact, visible, expiring grant.
Notes: One global login can hold independent organization memberships, but platform and tenant sessions never union.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#administrative-authority-and-nonprofit-operations
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-diagrams.md#11-administrative-surfaces-and-authority-boundaries

## Slide 9
CACHE ARCHITECTURE
Upstash improves shared-read performance without becoming system authority
MALLANET · MULTI-INCIDENT PLATFORM
09
Trusted resolver
Host + credentials + TenantScope + epoch
L0 / L1
Request + bounded process memory
L2 Upstash
Disposable shared result cache
Postgres
Authoritative scoped repositories
L3 edge
Cloudflare public HTTP cache
Every key includes environment + organization + incident + deployment/config + epoch + schema.
Always no-store
Auth · grants · support · cases · family/person/contact · consent · privacy operations
Separate systems
R2 media · Cloudflare Queues · BullMQ/Valkey · rate limits · sessions · approvals
Notes: Production and staging use separate Upstash Global databases. The provider can be disabled without changing public contracts.
[Sources]
- https://upstash.com/docs/redis/features/restapi
- https://upstash.com/docs/redis/features/consistency
- https://upstash.com/docs/redis/features/security
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#u34-upstash-distributed-cache-foundation-and-tenant-safe-invalidation

## Slide 10
ZERO-PLANNED-DOWNTIME MIGRATION
We build beside production, prove compatibility, then promote the exact tested version
MALLANET · MULTI-INCIDENT PLATFORM
10
BASELINE
Freeze exact main SHA
Colombia remains release source; continuous sync ledger starts.
EXPAND
Schema + compatible backend
Additive migrations, scoped writes, backfill, no destructive tighten.
PROVE
Old/new clients both ways
Stable client ↔ candidate API; candidate client ↔ stable API.
CANARY
Bounded traffic + soak
Verify build identity, isolation, queues, cache, and domain canaries.
CUTOVER
Final delta + route promotion
No DNS or database move; previous app version remains routable.
Any P0 during the cutover window aborts the cutover, lands in Colombia first, syncs, and restarts the soak clock.
Notes: The design targets zero planned downtime. It does not claim that the current single-host Compose path already provides it.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#final-delta-cutover-and-no-downtime-release
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#u19-live-colombia-change-intake-and-sync-ledger

## Slide 11
RELEASE SAFETY
Compatibility is tested in both directions before any release can advance
MALLANET · MULTI-INCIDENT PLATFORM
11
Candidate API
Stable API
Stable clients
Candidate clients
Required lane
Old public + admin clients must work
with candidate backend
Control lane
Stored stable artifacts prove
known behavior
Head/head lane
Candidate artifacts prove
new behavior
Required lane
Candidate clients must work
with stable backend
Release order: additive schema → compatible backend → admin/public clients → producers
Notes: [Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#verification-contract
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#u0-release-control-prerequisites

## Slide 12
CONTINGENCY MODEL
Failures stop the affected transition—not the live platform
MALLANET · MULTI-INCIDENT PLATFORM
12
Migration or lock failure
Fail closed. Keep current app live. Identify blocker read-only; retry in a safer window.
Cache or provider outage
Bypass to authoritative origin within budget. Disable optional module or cache; preserve contracts.
Isolation or privacy failure
Quarantine hostname/module, stop producers, advance epoch, purge, investigate as security incident.
Queue or channel failure
Stop new producers, preserve checkpoint/backlog, use old compatible consumer or verified manual channel.
Notes: The default rollback is code or routing rollback while additive schema stays in place—not database restoration.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#contingency-matrix
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#risks--dependencies

## Slide 13
PHASED ROADMAP
The roadmap proves foundations before expanding automation
MALLANET · MULTI-INCIDENT PLATFORM
13
PHASE A
Release controls
+ contracts
PHASE B
Tenant scope
+ Upstash
PHASE C–E
Modules, providers
+ catalogs
PHASE F
Rehearse +
cut over Colombia
PHASE G
Provisioning +
signals
PHASE H
Runtime sites +
admin + channels
Platform foundation
Colombia synchronization
Isolation + domain migration
Production rehearsal + cutover
Second-incident operability
Compatibility retirement
Entry gate for G/H: Colombia cutover and compatibility closure are complete, and a concrete second-incident driver is named.
Notes: This is sequence, not a promised calendar. Estimates come after the foundational inventory and execution-time main SHA are fixed.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#sequencing
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#goal-capsule

## Slide 14
RECOMMENDED NEXT STEP
The immediate decision is to fund and govern the safe foundation
MALLANET · MULTI-INCIDENT PLATFORM
14
Approve the architecture principles and authorize Phase A planning—not the full migration in one leap.
1
Name accountable owners
Platform architecture · Colombia sync · privacy/security · release operations
2
Freeze the execution baseline
Fresh immutable origin/main SHA; inventory contracts, caches, queues, schema, and workflows
3
Start the safety prerequisites
Immutable promotions, build identity, schema gates, mixed-version lanes, sync ledger
4
Return with evidence
Validated effort/risk estimate, rehearsal results, and a go/no-go package for migration
Success means faster response launch with no shortcut around tenant isolation, human approval, privacy, or rollback.
Notes: Close on a bounded approval: begin the prerequisites and evidence-gathering work, then return for the migration decision.
[Sources]
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-12-001-refactor-multi-incident-platform-plan.md#definition-of-done
- /Users/eduardomuthmartinez/Colombia/repo/docs/plans/2026-08-14-001-feat-platform-operability-plan.md#definition-of-done